| Project Title | Sheffield Street Tree Strategy Phase 1: Development |
| --- | --- |
| Subject to be worked on | Developing an exemplary Partnership Sheffield City Street Tree Strategy that values street trees for the benefits they bring to people, the city and the wider environment. |
| Where did the project come from, what need was identified? | From conflict and controversy over street tree management. To view street trees as an asset, providing ecosystem services such as improving air quality, reducing flood risk, supporting biodiversity & carbon sequestration. As an opportunity to agree a partnership approach to positively, actively and sustainably managing our street trees both now and for the long-term (200-300 years). As the ‘missing chapter’ of Sheffield City Council’s Tree & Woodlands Strategy In response to Defra’s recent consultation managing Trees & Woodland, and to demonstrate best practice |
| Objectives/Outputs | Agreed Partnership Strategy Vision & Aims for Sheffield’s Street Trees clearly demonstrating best practice Shared sense of ownership and joint working between partners and across the city’s communities Reference for others – potentially Planning Dept. Supplementary Planning Guidance. Agreed Partnership Delivery Plan for the initial 1-3 years Agreed Framework for longer-term delivery |
| Scope MUST = Critical to the project’s success. SHOULD = Important but not necessary for delivery in the current schedule timescales. COULD = Desirable requirements but not necessary. WON'T = won’t have time but would like in the future. | MUST include: (Critical to the project’s success) Theme 1 Key targets/aims eg optimise, maintain, increase canopy cover, natural capital, ecosystem services, or biodiversity net gain? All trees within the city’s highways network The value of trees Theme 2 An agreed and proportionate decision-making process for street tree management: including transparency, a balanced approach to risk assessment, cost/benefit analysis Species lists, with reference to resilience and climate change and suitability for the street environment An agreed process to identify and deliver additional/new planting Theme 3 Community involvement Agreeing current resources for delivery and identifying new resources Adoption process Partnership consensus and sign up to delivery plan Adoption by the Council SHOULD Influence other stakeholders about their approach to street tree design & management eg planning Exploring alternative approaches to street tree management long-term eg community management |
| Start Date Finish date | July 2019 until April 2020 |
| Timescales and interdependencies | No specific interdependencies identified but: STAG timeline for an agreed Strategy was for this spring summer = need for pace SCC process for adoption = 9weeks lead in |
| Risks | Disagreement and fallout between partners Risk rating: High Mitigation: Agree ‘ways of working’ and ‘terms of reference’ at first meeting, with clear understanding about red lines. Independent chair from SCC and STAG Other partners round the table bringing their own expertise and knowledge STAG/SCC monthly meetings Council won’t adopt partnership strategy Risk Rating: Low – medium Mitigation: Ensure Cllr Dagnall is fully involved and briefed. Encourage sounding board within the wider Cabinet Generate some early positive PR. Lack of resources and funding for delivery plan Risk rating; Low – medium External funding pots already exists Significant funding for tree management within the Streets Ahead contract Number of key partners involved with access to other resources |
| Opportunities | Increase resources and funding for city trees Through working as a partnership and with the community Realised by: delivery plan and partnership board Agreement and joint working between parties currently in conflict Realised by: working together for shared aims Reclaiming Sheffield’s place as THE Green City Realised by: developing and delivering the best Street Treet Strategy in the Uk. |
| Constraints | MUST comply with relevant legislation MUST be adopted by the Council – as street trees and road verges are the Council’s asset. MUST meet the requirements of the existing 18 years Streets Ahead contract, whilst also recognising opportunities to be flexible within this constraint |
| Has a project timeline been developed? For example using a GANTT chart (action plan timetable for the life of the project) | In outline: April 2020: Launch & start of delivery phase Jan 2020: Final version to all partners, including SCC to adopt Dec 2019: 95% Draft to partners Nov-Dec 2019: Drafting July – Oct 2019: Development/discussion and agreement/drafting based around the themes described under ‘scope’. |
| Has the project budget been agreed? | Paul Billington, SCC email confirmation: £5-10k for supporting Strategy Development eg expenses for ‘experts’, admin/secretariat support, materials, meeting spaces etc |
| Lead/Chair/Facilitator | Independent Chair: To provide oversight, facilitate, contribute and drive process. Seeking consensus, agreement and compromise. See ‘Terms of Reference’ Liz Ballard, SRWT |
| Who else needs to be involved? Describe their role. | Partnership Steering Group Members: To actively contribute, shape, develop, write the Strategy STAG: Paul Selby, Deepa Shetty, Christine King SCC: Mick Crofts, Karen Ramsay Amey: Darren Butt, Brian Stock Woodland Trust: Joe Coles, Urban Tree Officer Practitioner: Glen Gorner, Natural Environment Manager, Leeds CC (letter in hand to Leeds CC) Natural capital/value of trees expert: Dr Alison Holt Arbs specialist: Moray Simpson Specialists/Key Experts: To be invited in to bring specialist technical knowledge and experience at specific points in the process To be decided as required. Community of interest: To provide local input and knowledge from the community to help shape, develop, write the Strategy. To be consulted at specific milestones as the strategy develops eg forum, email Action: all, especially STAG & SCC, to start to draw together contact list for wider consultation during development phase. LB to including Community Dev input. |
| Agreed by Chair & Partnership Steering Group Members |  |

# Text boxes

Sheffield Street Tree Strategy

Development Phase

FINAL Project Set Up